## Sheet1
Project Name |  |  | Environment
Tester's Name |  | Ananyna Devanath | Reviewed By
Date Tested |  |  | Version
Issue Id | Module | Issue Title | Description | Steps to Reproduce | Issue Type | Priority | Severity | Actual Result | Expected Result | Attachment
1 | PIM(Contact detail) | Contact detail issue | Accepting more then 11 bd digits | 1.log in to Orange Hrm 2.Click PIM and add an employee 3.Click contact detail and add more then 11 digits | bug | medium | low | acceptance more then 11 digits | Not acceptance then 11 digits
2 | PIM(JOB) | Job specification field issue | Job specification field is not accepting any value | 1.login to Orange Hrm 2.Click PIM and add an employee 3.Click Job and add Job Specification | bug | medium | low | not allowing to input any job apecification | Allow to add any job specification
3 | PIM(job) | work experience related issue | work experience field should be mandatory | 1.login to Orange Hrm 2.Click PIM and add an employee 3.Click Job and add Job experience from | improvement | high | low | not a madatory field | should be a mandatory field
4 | PIM(job) | work experience related issue | work experience field should be mandatory | 1.login to Orange Hrm 2.Click PIM and add an employee 3.Click Job and add Job experience to | improvement | high | low | not a madatory field | should be a mandatory field
5 | PIM(Membership) | Subscription related issue | Subscription commence date adding mandatory | 1.login to Orange Hrm 2.Click PIM and add an employee 3.Click membership and add subscription | improvement | high | low | not a mandatory field | should be a mandatory field
6 | PIM(Membership) | Subscription related issue | Subscription commence date adding mandatory | 1.login to Orange Hrm 2.Click PIM and add an employee 3.Click membership and add subscription | improvement | high | low | not a mandatory field | should be a mandatory field